{"text_format":"3","workbook":"xls","n_sheets":5,"sheets":["上位机","跌落机硬件","会议记录","上传信息","上传记录"],"not_rendered":{"comments":3},"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"上位机","index":0,"n_rows":21,"n_cols":7,"rows_kept":21,"merged":[[0,0,0,6],[1,0,2,0],[1,1,2,1],[1,2,2,2],[1,3,2,3],[1,4,2,4],[1,5,2,5],[1,6,2,6],[3,1,4,1],[3,2,4,2],[5,1,6,1],[5,2,6,2],[7,1,8,1],[7,2,8,2],[9,1,10,1],[9,2,10,2],[11,1,12,1],[11,2,12,2],[13,1,14,1],[13,2,14,2],[15,1,16,1],[15,2,16,2],[17,1,18,1],[17,2,18,2],[19,1,20,1],[19,2,20,2]],"flags":["formulas_cached_only"]}
["SWD跌落设备上位机软件开发进度表"]
["Item","Process ","Status",null,"Start Date","Complete Date","Duration"]
[]
[null,"Customer design input preparation\nSWD提供设计输入准备","Open","Plan","2024-11-06","2024-11-07",2]
[{"$nulls":3},"Actual"]
[null,"TOPS依据设计输入制作软件界面及架构","Open","Plan","2024-11-08","2024-11-17",10]
[{"$nulls":3},"Actual"]
[null,"SWD确认评审软件界面,并签定确认书","Open","Plan","2024-11-18","2024-11-20",3]
[{"$nulls":3},"Actual"]
["OQC & Packing&Delivery","TOPS执行基于双方确定的软件界面的低层程式开发","Open","Plan","2024-11-21","2024-11-30",10]
[{"$nulls":3},"Actual"]
["OQC & Packing&Delivery","交付SWD确认并执行程式验证","Open","Plan","2024-11-25","2024-12-03",9]
[{"$nulls":3},"Actual"]
[null,"基于验证执行进一步的软件完善","Open","Plan","2024-12-03","2024-12-12",10]
[{"$nulls":3},"Actual"]
[null,"提交最终版本并交付SWD","Open","Plan","2024-12-13","2024-12-17",5]
[{"$nulls":3},"Actual"]
[null,"SWD最终验证完成并签署交付书，完成软件开发","Open","Plan","2024-12-18","2024-12-24",7]
[{"$nulls":3},"Actual"]
[null,"其它","Open","Plan","2024-12-25","2024-12-25",1]
[{"$nulls":3},"Actual"]

{"sheet":"跌落机硬件","index":1,"n_rows":17,"n_cols":10,"rows_kept":17,"merged":[[0,0,1,9]],"flags":["formulas_cached_only"]}
["SWD跌落设备通讯功能改造"]
[]
["项目","产品名称","改造内容","产品系列号","生产日期","SWD停机交付改造时间","SWD责任人","TOPS（返厂改造完成时间）","TOPS责任人","备注"]
[1,"贝尔两工位微跌试验机/BE-WD-2（非TOPS设备）","更换HMI触摸屏+PLC主件&编程软件+部份控制电路+RS485通信模块"]
[2,"高鑫微跌落试验机/GX-WDL12（非TOPS设备）","更换HMI触摸屏+PLC主件&编程软件+部份控制电路+RS485通信模块"]
[3,"华谊旋转微跌落试验机RS-DP-06S（非TOPS设备）","更换HMI触摸屏+PLC主件&编程软件+部份控制电路+RS485通信模块"]
[4,"TOPS微跌落试验机/MD-1","更换PLC主件/程序升级+485通信模块",20141029002,"2014-10-30"]
[5,"TOPS微跌落试验机/MD-1","更换PLC主件/程序升级+485通信模块",20141029003,"2014-10-30"]
[6,"TOPS耳机自由微跌落试验机/MD-4MSS","更换PLC主件/程序升级+485通信模块","2023102100418","2023-10-21"]
[7,"TOPS耳机电池自由微跌落试验机/MD-2HSS","更换PLC主件/程序升级+485通信模块","2020100600263","2020-10-09"]
[8,"TOPS二工位微跌落试验机MD-2MPS","更换PLC主件/程序升级+485通信模块","2018022600118","2018-02-28"]
[9,"TOPS微跌落试验机/MD-2PAM-AP（设备本身软硬件无需升级）","接驳通讯线缆（免费）","2023072700413","2023-07-29"]
[10,"TOPS耳机定向微跌落试验机MD-2HDD（设备本身软硬件无需升级）","接驳通讯线缆（免费）","2023072700411","2023-07-29"]
[11,"TOPS耳机定向微跌落试验机MD-2HDD（设备本身软硬件无需升级）","接驳通讯线缆（免费）","2023072700412","2023-07-29"]
[12,"TOPS耳机定向微跌落试验机MD-2HDD（设备本身软硬件无需升级）","接驳通讯线缆（免费）","2023102100417","2023-10-21"]
[]
[{"$nulls":5},"参会人签名："]

{"sheet":"会议记录","index":2,"n_rows":10,"n_cols":6,"rows_kept":10,"merged":[[0,0,0,7],[9,0,31,7]],"flags":["formulas_cached_only"]}
["SWD跌落设备上位机软件评审会议记录"]
[]
["会议时间：","2024/12/18；下午15：00",null,null,"会议方式：","腾讯会议"]
["参会人员：","SWD: 曾广宏，资慧，黄建光",null,null,"TOPS：章建军，陈义贤，黄志强"]
[]
["会议内容："]
["基于SWD前期针对上位机的设计要求，双方就初步完成开发设计并可实现初步功能的软件执行评估"]
[]
["SWD曾生：就现初步完成的软件功能，作以下新增或建议改善要求："]
["1.  针对“扫描样品条码-->1）自动连接到LIMS的数据库，读取样品条码对应的“项目代码，阶段，方案，工单名称”，或者2）扫描工单上的二维码，“项目代码，阶段，方案，工单名称” --> 选择“设备编号，通道号，跌落方向”--> 在触摸屏上点击启动测试。”                                                      TOPS回复：该项对软件编写工作量较大且关键在于贵司IT的积极配合；如能调动贵司IT积极配合，TOPS尝试去做，时间上也需留以充足时间到TOPS，该项需于2-3项完成验证OK后再行尝试。                                                                                                                                        2.针对“设备编号，通道号，跌落方向“这3项目上位机上以下“参数下发”方式，跌落次数，高度在触摸屏上； 要有互锁机制。或者上位机上只有“发送参数”，没有“启动”按钮。                                                                                                                        TOPS回复：TOPS现基于硬件配置初步评估仅可能可以做到：“设备编号，通道号，跌落方向”这3项目须上位机上完成输入，然后以“参数下发”方式发至跌落机PLC；然后跌落机设置“跌落高度，跌落次数，跌落速度”后启动执行；即上位机作样品基础数据输入及下发，跌落机输入基本参数点击启动执行；注：现在不增加成本下，触摸屏可以提示：1.当前跌落面（前提跌落方向固定）2.当前面测试已完成; 3.当前样品测试已完成。该项能力是否可做到，需要收到贵司跌落方向及跌落速度，跌落高度汇总信息后，PLC编程工程师&上位机软件工程时配合实际编写程式验证是否能实现，该能力验证阶段耗时约15-20天                                    \n3. 针对测试上传记录由原要求完成一个方向的目标次数后上传一次，改成每跌落一次上传相关记录参数一次;                                                                                                               TOPS回复：该项需要于项目2完成验证后，尝试购置多台PLC模拟多通道实际上传，依据实际效果状态评估可行性。                                                                                                                                                                                                                                 "]

{"sheet":"上传信息","index":3,"n_rows":5,"n_cols":3,"rows_kept":5,"merged":[[0,0,0,9],[1,0,3,0],[1,2,1,9],[2,2,2,9],[3,2,3,9],[4,2,4,9]],"flags":["formulas_cached_only"]}
["SWD跌落设备通讯上传信息"]
["业务需求","项目信息","以下四项称“项目信息”上位机软件能自动连接到LIMS的数据库，或扫描二维码方式直接读取；而不用人为输入。                                                                                                                                                                     1.目前已经提供了我们的数据上传通用接口给到供应商（之前给东博装备设备那个）\n2.需要上传设备信息如下（以下四项简称“项目信息”）：\n2.1 项目代码（如：APHxx或是X28xx）\n2.2 项目阶段（如：P1,EVT等）\n2.3 项目方案（如：AA,AB等）\n2.4 工单名称（如：Test 1，Test5等）\n"]
[null,"样品信息","以下四项简称“样品及设备信息”，由上位机软件界面输入                                                                                                                 2.5 设备编码 （如：SUN-LAB-Top-XXX；上位机软件界面选择输入)\n2.6 TestBuck SN （上位机扫码输入也可键盘上位机软件界面输入）\n2.7 设备通道号（如：通道1,2，键盘上位机软件界面选择输入）；\n2.8 跌落方向设定（如：正面，侧面，键盘上位机软件选择输入）；                                                                                                    "]
[null,"测试参数","以下三项简称“测试参数”，由触摸屏界面输入                                                                                                                                2.9 跌落次数 ：触摸屏界面设定；上传：方向次数（方单一跌落方向实时跌落次数），样品次数（单一样品跌落总数），通道累积数                                                                                                                                                                                      1>单方向跌落数：单个样品单个跌落方向的实时跌落次数（当达到方向设定跌落次数后停止并触摸屏上提示:“XX方向”跌落已完成 ，请更换方向）                                                                                                                                                                                                  2>单样品跌落总数：单个样品各个方向实时跌落数的总和（当达到各方向设定跌落次数总和后停止并触摸屏上提示:“所有方向”跌落已完成，请更换样品）                                                                                                                                                                                             3>通道累积总数：该通道测试里程（总累计数）数（当达到某一设定极限值或设价值的倍数后提示“跌落木板寿命已到”，请及时更换跌落木板）\n2.10 跌落速度 ：设备的跌落速度是以每分钟跌落多少次来计算的，比如20次/min\n2.11 跌落高度 ：上传每台设备的每个通道的跌落高度，比如75mm                                                                         \n\n"]
["应用场景","其它","2.12 测试开始时间 和 测试结束时间(PLC采集发至上位机）                                                                                                                                                                                                                                2.13 上传时间"]

{"sheet":"上传记录","index":4,"n_rows":24,"n_cols":17,"rows_kept":24,"merged":[[0,1,1,16]],"flags":["formulas_cached_only"]}
[null,"上传记录内容"]
[]
["中文","项目代码","项目阶段","项目方案或周次","工单名称","产品序列号","测试设备编码","设备通道","跌落方向","跌落高度(mm）","跌落速度(次/Min)","样品跌落次数","方向当前次数","木板累计跌落次数","开始时间","结束时间","上传时间"]
["英文","Project Code ","Project Phase","Config/WK","Work Order Name","Product Serial No.","Equipment Code","Device Channel","Orentation","Drop Height(mm）","Drop Speed（times/min)","Sample Drop Count","Orentation Drop Count","Particle Board Accumlated Drop Count","Start Time","End Time","Uploaded Time"]
[null,"APHxx","EVT","AA","Test5","asd-5214","SUN-LAB-Top-XXX",1,"正面",75,20,1,1,1,"2024-12-21  15:40:00","2024-12-21  16:40:00","2024-12-21  16:40:00"]
[null,"APHxx","EVT","AA","Test5","asd-5214","SUN-LAB-Top-XXX",1,"正面",75,20,2,2,2,"2024-12-21  15:40:01","2024-12-21  16:40:01","2024-12-21  16:40:01"]
[null,"APHxx","EVT","AA","Test5","asd-5214","SUN-LAB-Top-XXX",1,"正面",75,20,3,3,3,"2024-12-21  15:40:02","2024-12-21  16:40:02","2024-12-21  16:40:02"]
[null,"APHxx","EVT","AA","Test5","asd-5214","SUN-LAB-Top-XXX",1,"正面",75,20,4,4,4,"2024-12-21  15:40:03","2024-12-21  16:40:03","2024-12-21  16:40:03"]
[null,"APHxx","EVT","AA","Test5","asd-5214","SUN-LAB-Top-XXX",1,"正面",75,20,5,5,5,"2024-12-21  15:40:04","2024-12-21  16:40:04","2024-12-21  16:40:04"]
[null,"APHxx","EVT","AA","Test5","asd-5214","SUN-LAB-Top-XXX",1,"反面",75,20,6,1,6,"2024-12-21  15:40:05","2024-12-21  16:40:05","2024-12-21  16:40:05"]
[null,"APHxx","EVT","AA","Test5","asd-5214","SUN-LAB-Top-XXX",1,"反面",75,20,7,2,7,"2024-12-21  15:40:06","2024-12-21  16:40:06","2024-12-21  16:40:06"]
[null,"APHxx","EVT","AA","Test5","asd-5214","SUN-LAB-Top-XXX",1,"反面",75,20,8,3,8,"2024-12-21  15:40:07","2024-12-21  16:40:07","2024-12-21  16:40:07"]
[null,"APHxx","EVT","AA","Test5","asd-5214","SUN-LAB-Top-XXX",1,"反面",75,20,9,4,9,"2024-12-21  15:40:08","2024-12-21  16:40:08","2024-12-21  16:40:08"]
[null,"APHxx","EVT","AA","Test5","asd-5214","SUN-LAB-Top-XXX",1,"反面",75,20,10,5,10,"2024-12-21  15:40:09","2024-12-21  16:40:09","2024-12-21  16:40:09"]
[null,"APHxx","EVT","AA","Test5","asd-5215","SUN-LAB-Top-XXX",1,"正面",75,20,1,1,11,"2024-12-21  15:40:10","2024-12-21  16:40:10","2024-12-21  16:40:10"]
[null,"APHxx","EVT","AA","Test5","asd-5215","SUN-LAB-Top-XXX",1,"正面",75,20,2,2,12,"2024-12-21  15:40:11","2024-12-21  16:40:11","2024-12-21  16:40:11"]
[null,"APHxx","EVT","AA","Test5","asd-5215","SUN-LAB-Top-XXX",1,"正面",75,20,3,3,13,"2024-12-21  15:40:12","2024-12-21  16:40:12","2024-12-21  16:40:12"]
[null,"APHxx","EVT","AA","Test5","asd-5215","SUN-LAB-Top-XXX",1,"正面",75,20,4,4,14,"2024-12-21  15:40:13","2024-12-21  16:40:13","2024-12-21  16:40:13"]
[null,"APHxx","EVT","AA","Test5","asd-5215","SUN-LAB-Top-XXX",1,"正面",75,20,5,5,15,"2024-12-21  15:40:14","2024-12-21  16:40:14","2024-12-21  16:40:14"]
[null,"APHxx","EVT","AA","Test5","asd-5215","SUN-LAB-Top-XXX",1,"反面",75,20,6,6,16,"2024-12-21  15:40:15","2024-12-21  16:40:15","2024-12-21  16:40:15"]
[null,"APHxx","EVT","AA","Test5","asd-5215","SUN-LAB-Top-XXX",1,"反面",75,20,7,7,17,"2024-12-21  15:40:16","2024-12-21  16:40:16","2024-12-21  16:40:16"]
[null,"APHxx","EVT","AA","Test5","asd-5215","SUN-LAB-Top-XXX",1,"反面",75,20,8,8,18,"2024-12-21  15:40:17","2024-12-21  16:40:17","2024-12-21  16:40:17"]
[null,"APHxx","EVT","AA","Test5","asd-5215","SUN-LAB-Top-XXX",1,"反面",75,20,9,9,19,"2024-12-21  15:40:18","2024-12-21  16:40:18","2024-12-21  16:40:18"]
[null,"APHxx","EVT","AA","Test5","asd-5215","SUN-LAB-Top-XXX",1,"反面",75,20,10,10,20,"2024-12-21  15:40:19","2024-12-21  16:40:19","2024-12-21  16:40:19"]